## Slide 1: Prototyping high performance computing API to deposit and recover datasets - Kickoff Meeting Contract# - S15-072
April 8th, 2014

## Slide 2: Agenda
Introduction
Objectives
Scope & Tasks
Key Stakeholders/Customers
Project Team Organization
Deliverables
Subcontracting/Invoice Procedures
Technical Points and Expectations
Risks and Dependencies
Communication
Open Questions

## Slide 3: Introduction
NCI
  Carl McCabe
  Government Sponsor
    Chief, Informatics and Scientific Computing Services Branch US National Cancer Institute’s Center for Bioinformatics & Information Technology
    Phone: 240-276-7366
Email: Carl.McCabe@nih.gov

## Slide 4: Introduction
Leidos Biomedical Research, Inc. (LBR)
  Eric A Stahlberg – LBR ISP HPC Strategy Director
    Information System Program Directorate
    High-Performance Computing Strategy
    Phone: 240.276.6729
    stahlbergea@mail.nih.gov
  Zhengwu Lu – LBR TPM
    Technical Project Manager, Information System Program Directorate
    Phone: 240-276-6487
    Zhengwu.Lu@nih.gov
  Matt Costello – LBR Subcontracts Administrator
    Research Subcontracts
    Phone: 301-846-6828
    matthew.costello@nih.gov
  Alexander Konev – LBR Contracting Officer
    Research Subcontracts
    Phone: 301-228-4323
    konevas@nih.gov

## Slide 5: Introduction
SVG Resources
  Prasad Konka – POC, Software Architect
    Phone: 703-431-1134
    Prasad.konka@gmail.com
  Eran Rosenberg – Scrum Master, Developer
    eran.rosenberg@nih.gov
  Mahi Narra – Software Developer
  Durga Addepalli – Business Systems Analyst

## Slide 6: Primary Objective
Establish new highly-reliable service to support management of mission critical and archival data
Motivations
  Ease the burden of individualized data management
  Enable greater value derived from generated data and datasets
  Facilitate compliance with emerging data sharing requirements
  Be more cost effective with purchases of storage

## Slide 7: Secondary Objectives
Improve ease of use near-term and long-term
  Provide stable means to deposit, access and recall managed data from the investigator and analyst perspective
  Support mechanisms to annotate datasets
  Position to align internal efforts with BD2K efforts
  Technology agnostic interface for users of system
Derive greater value from datasets
  Make metadata searchable
  Enable extensions to metadata fields
  Support remote access to available metadata

## Slide 8: Secondary Objectives
Facilitate compliance with emerging data sharing requirements
  Enable migration of datasets seamlessly to meet policy requirements
  Foster utilization of external resources for sharing
Be more cost effective
  Reduce unneeded copies of large datasets
  Enable migration/staging of data to appropriate storage based on utilization
  Improve dataset reuse based upon past dataset experiences

## Slide 9: Scope
Establish services to support the general transfer of large datasets without requiring physical mounting.
Establish a pilot data set registration system to associate a label with a given managed dataset.
Establish easy-to-use methods for providing annotation information.
Establish a high-reliability storage model.
Obtain utilization statistics.
The developed APIs, associated dataset object repository, metadata and registration catalog database shall empower CBIIT in unifying its IT services, infrastructure and high performance computing architecture throughout NCI to support NCI enterprise business needs.

## Slide 10: Tasks
Program Management
  Source code repository, potentially GitHub
  Project feature/backlog tracking, potentially custom JIRA
  Monthly technical and financial reports
  Status Meetings (weekly and as needed)
  Project Summary Report
Prototyping Tasks
  Requirements gathering and use case development
  Plan to meet with 7 investigators/advisors in the month of
  April 2015, prepare high level business use cases in: NGS
  DNA, RNA, proteomics, or imaging analysis

## Slide 11: Tasks
Prototyping Tasks
  Assess technology
  Design, prototyping, testing and implementation of proposed APIs
  Analyze, conceptualize and design associated metadata, registration catalog database for the central HPC datasets object archive
  Implement: Agile development approach with feature sets to be determined for development, demonstration, and testing in sprints
  Provide HPC API/CLIs documentation as appropriate: User Guide, Technical Guide, Installation Guide, and Design Documentation.

## Slide 12: Key stakeholders
Key Stakeholder | Team Member
NCI Government Sponsor (GS) | Carl McCabe
LBR ISP HPC Strategy Director | Eric Stahlberg
LBR Technical Project Manager (TPM) | Zhengwu Lu
Subcontractor Point of Contact | Prasad Konka
SVG Team | Prasad Konka, Software Architect Durga Addepalli – Business Systems Analyst Mahi Narra – Software Developer Eran Rosenberg – Scrum Master, Developer

## Slide 13: Project Team Organization
Project Organizational Structure

## Slide 14: Deliverables
DELIVERABLE | DUE DATE
Project Deliverables | 
Monthly Technical and Financial Status Reports | 10th of each month
Project Summary Report | No later than 10 Days Before Project Completion
API Requirements Specification, API Design Specification, Metadata/Catalog Organization Specification | No later than 10 Days Before Project Completion
Software Codebase | No later than 10 Days Before Project Completion

## Slide 15: Subcontracting
LBR Roles and Responsibilities
  Contracting Officer
  Only the Contracting Officer has authority to: (1) direct or negotiate any changes to the Statement of Work; (2) modify or extend the period of performance; (3) change the delivery schedule; (4) authorize reimbursement to the Subcontractor of any costs incurred during the performance of this subcontract; or (5) otherwise change any terms and conditions of this subcontract. All changes to the Statement of Work will be accomplished by bilateral modification to the subcontract.
  Only the Contracting Officer as named above shall have the authority to prescribe changes to this subcontract or provide direction for which the Subcontractor will seek reimbursement. Any costs incurred by the Subcontractor not delineated herein or without the prior written approval of the Contracting Officer are incurred at the Subcontractor’s significant risk of non-payment.

## Slide 16: Subcontracting
LBR Roles and Responsibilities
  Contracting Officer’s Technical Project Manager (TPM)
  The Contracting Officer’s TPM is responsible for: (1) monitoring the Subcontractor’s technical progress, including the surveillance and assessment of performance and recommending to the Contracting Officer changes in requirements; (2) interpreting the Statement of Work and any other technical performance requirements; (3) performing technical evaluation as required; (4) performing technical inspections and acceptances required by this subcontract; and (5) assisting in the resolution of technical problems encountered during performance.
  Neither the TPM nor any person or entity other than the Contracting Officer possess any authority, implied or apparent, to provide direction that may cause or influence the Subcontractor to incur additional costs for which reimbursement may be sought. Any costs incurred by the Subcontractor not delineated herein or without the prior written approval of the Contracting Officer are incurred at the Subcontractor’s significant risk of non-payment.
Notes: 16

## Slide 17: Subcontracting
LBR Roles and Responsibilities
  Subcontracts Administrator
  Serves as liaison between SVG and the LBR TPM. Additionally is responsible for administering, processing and handling contractual documentation.
Notes: 17

## Slide 18: Invoice Procedures
    Subcontractor POC prepare Monthly Status Reports – MSR (technical and financial)
    Send to LBR TPM, Subcontracts Administrator
    LBR TPM review, comment and approve MSR
    Subcontractor receive and address comments from LBR TPM
    Subcontractor send invoices monthly to LeidosBiomed@invoices.corcentric.com and cc: LBR TPM upon MSR approval (by LBR TPM)

## Slide 19: Technology Points
Phase 1 – Robust, available and supportable
Phase 2 – Performance and optimization
Phase 3 – Technology change-out, extensibility and enhancements
Leverage existing technologies that meet technology constraints while fulfilling use case needs
Examine existing models for archive data management
Expect technologies to change
Object store technologies, NoSQL technologies, and more

## Slide 20: Phase 1 - Aims
Define stable interface that meets near-term and long-term basic needs
  Archive placement of dataset
  Registration of dataset
  Basic annotation of dataset
  Location of datasets
  Recall of datasets
A façade that is agnostic of underlying technology implementation
Robust and reliable as a core service
Designed for evolution of underlying technologies
Keep it simple

## Slide 21: Phase 1 – Additional Topics
Data security
  Inherent to protect the data placed in trust with the service
Data sharing
  Prove utilization of other services being created for data sharing
Extensive metadata
  Prove ability to support secondary metadata indexes
Dataset types
  Agnostic of datatype
  Driving initial use cases in genomics, imaging and biophysics

## Slide 22: First Focus Areas in Phase 1
Use case information capture
Initial technology option selection
Draft interface definition
  Leverage popular and de-facto standard interfaces to advise features (e.g. Amazon S3, Red Hat, etc.)
  Describe use case scenarios using interface definitions
  LBR TPM and the Subcontractor shall develop a feature set based schedule as needed and delivery of project deliverables
Keep it simple

## Slide 23: Technical Expectations
Leidos TPM acts as key technical and customer focal point to perform project management, scheduling and arrange demonstrations
Subcontract POC works with BSA/Developers to ensure timely deliverable of required documents and contract deliverables.
Subcontract POC communicates with LBR TPM for guidance and direction on any issues that arise.

## Slide 24: Risks and Dependencies
Risk / Dependency | Rating | Mitigation
Key personnel leave the program during POP. | Low | Provide supportive subcontractor management; work with LBR TPM to identify replacement resource.
The SVG team do not meet the timeline for required deliverables. | Medium | Work with SVG POC and members to establish a schedule for development as needed and delivery of project deliverables; communicate with SVG after each meeting to ensure team is meeting the planned schedule.
Scheduling of interviews and granting of access to infrastructure is delayed or blocked delays the timeline for required deliverables. | Medium | LBR TPM and LBR HPC Director to ensure rapid and effective communication with interviewees and slotting of interviews ASAP; also work on granting access to physical infrastructure for technical assessment/prototyping.

## Slide 25: Communication
Meetings
  Project Kick-off
  Weekly Status Meeting
  Meetings as Needed (Review Meetings, Individual Meetings, Task Review Board Meeting)
Ad-hoc meetings requested by LBR TPM
Project communication via potential custom JIRA tracker system
  Consult with LBR ITOG/system team

## Slide 26: Open Questions
Project Wiki location, development and maintenance
    This may be unnecessary
    ?